## Crosscutting
ANNEX B ACTION PLAN
| CROSSCUTTING | These actions will be replicated for each of the priority sectors | [5 empty] | Short= 3-6 months Medium= 6-12 months Long= 12 months plus
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics/Monitoring | Timescales | Who | Progress | Next Steps | RAG | Impact
1 | Clearer pathway into priority sectors |  | A clear and consistent mapping of career pathways | A robust end to end clear career pathway Provision mapped to stages on the pathway |  | Availability and distribution |  |  |  |  | Amber | Economic retention: By training local people for local priority sectors, wealth is kept within the region, preventing talent drain to surrounding regions. Systemic inclusion: Drastically reduced structural unemployment, moving vulnerable or disproportionately affected demographics into resilient, future-proof, and high-paying jobs. Place-based economic growth: The priority sectors become highly competitive, driving regional productivity and cementing the area’s reputation as an innovative economic anchor.
|  | Identify stakeholders and existing programmes of work | To validate any data or hypotheses and co-design pathways - Create working group for ongoing development - Map current programmes Promotion of completed pathways | A representative group of stakeholders to inform, innovate and promote the sector | Task and finish group set up | Reporting from task and finish group | Short | Sue Taylor (Passport) Careers Hub Employers (3?) ERB SA FE/HE | Sue Taylor has undertaken mapping pilot as part of Professional Baccalaureate pilot - ERB undertaken own mapping work - Careers Hub has completed mapping exercise | Initial meeting with Careers Hub/Sarah Randall - Identify wider stakeholders and convene - Consolidate existing mapping exercises - Present draft pathway/validate with employers and providers | Amber
|  | Establish baseline available provision | To set a benchmark and understand where the gaps are and what the takeup is | Baseline position of current provision | Baseline data | Number of courses available and % of uptake | Short | Careers Hub Employers (3) ERB SA FE/HE |  | Utilise data from ASF to understand provision available for AY 26/27 - Utilise data from Skills Bootcamps provision | Amber
|  | Understand skills needs | Clear understanding of the skills needs in each sector | Clear skills map aligned to progression pathways | Completed skills needs map | Report compiling output of skills mapping and needs analysis | Short | Commissioned provider? ERB/SA Employers |  | Conduct indepth research with a range of employers (potentially commissioned service) | Amber
|  | Identify skills gaps | Clear picture of gaps in provision | Map of gaps for use in commissioning |  | Gap analysis data | Short/Medium | Careers Hub Employers (3) ERB SA FE/HE |  | Collate combined baseline provision and cross reference to the draft pathways | Amber
|  | Draft a career pathway document | A consistent format of career pathways | Agreed and validated pathway document | Initial draft | Confirmation of completion of document | Short/Medium | Careers Hub Employers (3) ERB SA FE/HE Additional employers and schools |  | Agree format for the template (dependent on media) - Compile initial draft - Validate/test | Amber
|  | Distribution and publication of career information | County wide use and sharing | Final career pathway document | Final draft available | Distribution and use | Medium | Careers Hub Colleges and schools |  |  | Amber
2 | Raising awareness and profile of priority sectors |  | More people entering into the sector | Marketing and communication of roles in the sector |  | Course provision data LMI data on vacancies |  |  |  |  | Amber | Mitigation of talent drain: raising the profile of high-value, domestic digital and green tech clusters keeps talent within the county. Socio-Economic Inclusion: Pockets of deprivation across Surrey are tackled by creating accessible, visible, and lucrative ladders of opportunity for all residents. Increased Economic Resilience: Cementing Surrey’s position as a premier, high-value knowledge economy, which attracts inward corporate investment due to a visibly deep, localized talent pool.
|  | Identify Target audience | Clear audience map (including target demographics, e.g. young people, women, economically inactive) - Clear routes to engage targets | Audience/stakeholder map | Audience/stakeholder map completed including action plan | Confirmation of completed map and action plan | Short | DWP/jobcentres Connect to work STEP Careers Hub Employers Schools and Colleges |  | Engage with identified stakeholders - develop map of target groups and routes to engage | Amber
|  | Review Construction package for best practice (Wilmott Dixon) | Take learnings from it | Further developed action plan on how to reach target audience |  | Report on Construction package project | Short | ERB/SA |  | ERB to obtain data and findings from Wilmott Dixon | Amber
|  | Co-design employer messaging | Clear understanding of messaging - Clear understanding of media choices and audience requirements | Selection of outputs to be used in media campaign | Messaging confirmed | Material completed | Short | Employers ERB/SA |  | ERB to engage with employers to inform co-design of messaging | Amber
|  | Identify potential funding sources | Fully funded campaign package | Finances | Funding secured | Reporting from ERB | Short | ERB/SA |  | ERB/SA to consider options to explore | Amber
|  | Create campaign/content | Initial set of materials for review | Package of mixed media for distribution | Material available | Distribution and use | Medium/Long | Stakeholders above plus Task and Finish group |  | Early engagement with Tim Ridgway to support | Amber
|  | Distribution and publication | Increase in messaging on the sector and pathways |  |  |  | Medium/Long | Stakeholders above plus Task and Finish group |  |  | Amber
3 | Increase capacity in teaching staff |  | Increase in sector specific teaching capacity |  |  | Vacancy data Anecdotal feedabck from colleges |  |  |  |  | Amber | Maximized Devolved Funding Return: Directly satisfies the DfE/DWP growth missions by converting capital investment into a measurable drop in local vacancies. Sustainable Local Employment: Protects Surrey's workforce from displacement, establishing a resilient county-wide ecosystem where public funding constantly aligns with business growth.
|  | Identify stakeholders needed to deliver actions | Ensuring the right people are involved to deliver the actions | Stakeholder group | Stakeholder group identified and created | Reporting from stakeholder group | Short | Sector specific employers FE/HE Skills for jobs ERB SA |  | ERB/SA to engage with Surrey FE - SA to feedback on prospective Skills Bootcamps provision aligned to this target | Amber
|  | Identify baseline of current gaps | Focus scope of activity | Gap analysis |  | Report highlighting gaps | Short |  |  | Stakeholder group to utilise network and data from ASF/Bootcamps/wider provision | Amber
|  | identify schemes to increase capacity of teaching staff | Awareness of best practice and opportunities to collaborate | Report and recommendations |  | Report on current schemes | Short |  |  |  | Amber
|  | Further actions to be taken following engagement with key stakeholders | Support for schemes that will increase specific teaching capacity |  |  | Finalised report summarising current picture and making recommendations - Updated action plan | Medium
.

## Priority 1
| PRIORITY 1 – Increase pipeline of technical skills feeding into key manufacturing and engineering sectors | [5 empty] | Short= 3-6 months Medium= 6-12 months Long= 12 months plus
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
1 | Improve entry to, progression and retention in engineering and manufacturing including defence relevant occupations |  | More people in the sector progressing in their roles
|  | Refer to Crosscutting actions relating to "pathways into priority sectors" | Raised awareness of pathways into entry level roles |  |  |  | Medium
|  | Co-design progression focused pathways | This will be developed futher ahead of completing the "entry to" work |  |  |  | Medium/Long | Skills for Jobs FE/HE Made Smarter
2 | Pilot a shared recruitment and workforce talent pool |  | Opportunity not to lose talent from the pipeline and provide a central repository for the sector to recruit from
|  | Engage with McLaren | Understand the scope and expectations |  |  |  |  | McLaren ERB SA
|  | Run pilot initiative with McLaren | Develop a first pass to identify best practice
|  | Review pilot | Find opportunities to refine the system
|  | Develop best practice | Develop a consistent approach that delivers high quality outcomes
|  | Engage wider employer network | Expansion of offer that promotes a cohesive approach
.

## Priority 2
| PRIORITY 2 – Increase pipeline of construction skills, including for the green transition | [5 empty] | Short= 3-6 months Medium= 6-12 months Long= 12 months plus
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
1 | Improve the availbility of a skilled workforce for key construction activities |  | Stable pipeline Improved progression pathways
|  | Refer to Crosscutting Action 1 | A clear and consistent mapping of career pathways |  |  |  | Short
|  | Refer to Crosscutting Action 2 | More people entering into the sector |  |  |  | Medium/Long
|  | Convene Construction Steering Group | Leaders in industry to share how they recruit and retain their workforce Leaders in the industry and sharing best practice with SMEs Increased awareness of progression routes and training opportunities A more equipped workforce is developed
|  | Plan and schedule supply chain engagement events | Increasing perception of the sector Raise awareness training opportunities |  |  | SME numbers and engagement surveys
Deliver exchange events (speak to Wilmott Dixon)
|  | Engage with SurreyFE about Ready to Learn and Ready to Work programmes | Promotion of these events to residents
2 | Improve progression and retention in specialist roles |  | More people able to progress in the sector
|  | Refer to Crosscutting Action 1 | A clear and consistent mapping of career pathways | A robust end to end clear career pathway Provision mapped to stages on the pathway |  |  | Short
|  | Refer to Crosscutting Action 2 | More people entering into the sector |  |  |  | Medium/Long
|  | Marketing activity additional to CA2 | Further increase progression of existing workforce | Tailored marketing materials
3 | Embed sustainability and green skills across all aspects of the sector |  | Greater fundamental knowledge of green skills at all levels of an organisation
|  | Stakeholder mapping | Ensuring the right people are involved to deliver the actions | Stakeholder map |  |  |  | Activate Learning Employers Providers HE
|  | Baseline of provision and support available | Identify gaps in provision | Baseline data
|  | Co-design suitable curriculum | Curriculum that provides the fundamental knowledge required | Curricula
|  | Awareness activity | Increasing the appetite for sustainbility and green skills training | Marketing materials Waiting list for course sign-up |  | Marketing engagement Enquires received Waiting list numbers
|  | Pilot with a selection of employers | Delivery of training and development of case studies | Case studies |  | Case studies Business impact
|  | Refinement of curricula | Finalised curricula
|  | Transfer to BAU/launch | Courses are now available for sign-ups | Available course |  | Number of sign-up/completions Learner feedback Business impact
.

## Priority 3
PRIORITY 3 – Improve recruitment, retention and development within the Social Care sector
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
| Support the expansion of related provision e.g. Skills bootcamps |  | More people going into social Care
Identify the skills needed to be taught in pre-employment training
Create provision that meets the skills needed
| Increase workplace experience opportunities for social care roles |  | Stronger sustained partnerships between education providers and employers
Convene our established Social Care Forum
Working with tools from Skills for Care and Surrey care Association co-ordinate placement brokerage
| Strengthen business development support for care businesses |  | Improved leadership capability and strategic workforce development
Provide coaching, training and mentoring via the Surrey Care Association
| Strengthen digital capability of Social Care sector |  | Improved delivery of services needed within the sector
.

## Priority 4
PRIORITY 4 – Support workplaces and workers to build the foundations and infrastructure needed to confidently adopt existing and emerging digital tools
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
| Understand the challenges faced by SMEs around use of technology |  | By understanding the challenges we can find solutions to enable higher rates of adoption and improved productivity
|  | Carry out research into the challenges | Identify roadblocks |  |  |  |  | University of Surrey ERB
Deliver templates and how to guides to overcome challenges
| Map existing local and national training already available | [6 empty] | University of Surrey ERB
Identify gaps and propose ways of filling those gaps
| Support businesses to assess their own capability through a simple diagnostic tool |  | Tailored feedback would be available to speed up the adoption of digital skills
Convene a task and finish group to co-design, pilot and deliver the tool
.

## Priority 5
PRIORITY 5 – Improve work-ready employability skills and generic digital skills
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
| Co-design a Surrey-wide standardised employability skills package |  | A consistent baseline of employability skills preparing young people for the workplace, resulting in them bringing higher levels of productivity
Convene a Task and Finish group to co-design the package
Ensure that employers are part of the design process
Incorporate basic AI skills within the package
Work with HE to adapt the package for older students
Deliver the package into schools colleges and Universities
| Create a campaign to encourage more availability of real work placements |  | Create an environment where employers can easily offer placements and do so
Co-ordinate the campaign across all relevant organisations
Recruit champions of work placements to help get the message out
Link in with the sector work in the Crosscutting actions
| Prepare young people to start up their own business straight from education |  | More successful businesses starting up but even if they decide not to start up the support would help them in employment
Convene a Task and Finish group to design a "Start up Skills" package
Incorporate Sales skills within the package
Promote through education but also through JCP
Identify funding to deliver to cohorts
.

## Priority 6
PRIORITY 6 – Increase employer engagement, awareness and commitment to skills development
Number | Priority | Actions | What are our desired outcomes | Outputs | Milestones | Metrics | Timescales | Who | Progress | Next Steps | RAG | Impact
| Increased curriculum integration between providers and employers |  | A curriculum that is aligned with the needs of the employers
|  | Create regular opportunities for employers to feed into curiculum conversations (based on sector groups) | Employers work more closely with providers and are more confident in investing in skills they need
| Increased engagement of employers |  | Employers are better informed about skills needs, provision and available support and therefore do better workforce planning
|  | Share key labour market intelligence, opportunities and other important messages through a quarterly newsletter and an annual skills Conference | Stronger feedback loops between employers and providers
|  | Use current on-line tools to increase engagement (e.g. future skills hub, STEP surrey) | Employers engagement in the local skills system becomes more sustained rather than one off offers of support
|  | Deliver monthly newsletter to promote events and new courses | Opportunities are taken up and more engagement occurs
Better recruitment practices through access to untapped talent pools
|  | Co-ordinate employer engagement with untapped talent initiatives such as Connect to Work | Avoid duplication of reaching out to employers by linking all initiatives and create a co-ordinated "ask"
|  | Promote inclusive recruitment practices | Improve knowledge and awareness of Employers on what is available to them when solving recruitment issues
|  | Create targeted recruitment events | Enable more individuals to be employed and employers to find a recruit